PROJECT DELIVERY ROADMAP

GitStack

Confirmed team for the 1 August restart

Core A / Team Lead: Jubair Ahmed Efty
Core B: Shabab Ahmed
Support: Siam Ibne Sarwar

Fixed delivery dates: 50% demonstration: 1 September 2026 ¦ 100% demonstration and faculty submission: 22 September 2026

Roadmap window

Saturday, 1 August - Tuesday, 22 September 2026

Baseline v1.1  |  Team assignments confirmed 29 July 2026

# How to use this roadmap

This document replaces the old date plan. Work completed before 1 August may remain in repository history for safety, but it does not count as evidence for the new schedule. Every scheduled item must produce new evidence: an issue, branch, commit, test result, reviewed pull request, or demonstration artifact.

Delivery outcome: A functional GitStack MVP that teaches Git, provides an isolated practice terminal, supports one real collaborative workflow, automatically assesses the workflow, and gives useful student and instructor reports.

## Contents

- 1. Fixed constraints and planning assumptions

- 2. MVP scope and demonstration definitions

- 3. Team roles and ownership

- 4. Branch, review, and integration workflow

- 5. Dated roadmap: 1 August - 22 September

- 6. Demonstration scripts and release gates

- 7. Definition of Done, quality controls, and risks

- 8. How the team will work with ChatGPT during execution

- 9. First-day checklist

Important interpretation: A fresh start is a planning and delivery reset, not permission to erase Git history. Preserve the existing repository. Archive or tag the pre-reset state, then create new reset issues and branches from the agreed baseline.

# 1. Fixed constraints and planning assumptions

| Constraint | Decision | Operational meaning |
| --- | --- | --- |
| Start | 1 August 2026 | All roadmap evidence begins on this date. |
| 50% gate | 1 September 2026 | A stable vertical slice must be demonstrated. |
| 100% gate | 22 September 2026 | The MVP must be complete and submission-ready. |
| Core team | Jubair Ahmed Efty and Shabab Ahmed | Core A and Core B own all critical-path work. |
| Support | Siam Ibne Sarwar | Support handles selected, bounded tasks; no critical dependency. |
| Development | Separate member task branches | Members work independently within assigned ownership. |
| Integration | develop plus protected main | Reviewed release PRs enter main; nobody pushes directly. |

## Planning capacity

The schedule assumes Jubair Ahmed Efty (Core A / Team Lead) and Shabab Ahmed (Core B) can each contribute about 12-15 focused hours per week, and Siam Ibne Sarwar (Support) about 4-6 hours per week. These are planning assumptions, not confirmed availability. If the team cannot sustain them, reduce optional scope immediately rather than sacrificing security, testing, or integration.

- Work-in-progress limit: one active implementation issue per core member.

- Every seven-day block includes at least one integration, testing, or buffer session.

- The supporting member receives no more than one bounded assignment at a time.

- A task is not complete merely because code exists; it must satisfy the Definition of Done.

# 2. MVP scope and demonstration definitions

The roadmap prioritizes a narrow end-to-end product over a large collection of incomplete pages. The fixed product flow is: Learn Git -> Practise Safely -> Work in Teams -> Follow a Real Workflow -> Receive Automatic Assessment.

| Capability | Required on 1 September | Required on 22 September |
| --- | --- | --- |
| Repository and local stack | Working, repeatable setup | Hardened, documented release setup |
| Accounts and roles | Student login; instructor access for demo | Student/instructor role guards and clean error handling |
| Learning experience | Small Git Basics lesson and mission catalogue | Polished EN/BN content for the required MVP flow |
| Practice terminal | xterm connected to one isolated Docker sandbox | Reliable lifecycle, cleanup, limits, and recovery |
| Single-user mission | One deterministic mission works end to end | Retained as a tested onboarding mission |
| Assessment | Rule-based final-state checks and basic feedback | Workflow rules, Bangla feedback, individual/team scores |
| Progress | Attempt and completion stored in PostgreSQL | History and reports available to students/instructors |
| Collaboration | Architecture proof only; not the demo focus | One deterministic Gitea-backed team mission |
| Instructor view | Basic attempt list | Dashboard, team status, reports, reset/retry controls |

## Required MVP

- Next.js/React frontend with Tailwind CSS and xterm.js.

- Node.js/Express API with a WebSocket or PTY bridge for the terminal.

- PostgreSQL with Prisma migrations and seed data.

- Per-user Docker sandbox with strict resource and privilege controls.

- Gitea integration for one real team workflow.

- Deterministic, rule-based assessment; no fabricated AI intelligence.

- Student progress, individual/team reports, and an instructor dashboard.

- English/Bangla feedback for the assessed workflow.

## Explicitly out of scope until the MVP is stable

- Leaderboards, badges, social features, chat, and gamification extras.

- Large lesson libraries or many collaborative missions.

- Social login, email verification, payments, or mobile applications.

- Generative-AI feedback; the MVP uses explainable rules.

- Advanced analytics, plagiarism detection, and public multi-tenant hosting.

Scope rule: Never cut authentication controls, sandbox isolation, automated tests, or recovery behavior to make room for optional features.

## Target architecture

| Layer | Main component | Responsibility |
| --- | --- | --- |
| Web | Next.js, Tailwind, xterm.js | Lessons, mission UI, terminal, reports |
| API | Express and WebSocket/PTY bridge | Auth, mission lifecycle, terminal sessions |
| Data | Prisma and PostgreSQL | Users, teams, missions, attempts, scores |
| Sandbox | Docker orchestrator | Per-user containers, limits, cleanup |
| Collaboration | Gitea and its API | Repositories, branches, pull requests, reviews |
| Assessment | Deterministic rule engine | Git-state and workflow-event evaluation |

# 3. Team roles and ownership

Confirmed team: Jubair Ahmed Efty is Core A and Team Lead; Shabab Ahmed is Core B; Siam Ibne Sarwar is Support. The dated schedule uses their first names beside every assigned task for fast tracking.

| Role and member | Primary ownership | Typical deliverables |
| --- | --- | --- |
| Core A Jubair Ahmed Efty Team Lead | Team lead, platform, integration | Express API; Prisma/PostgreSQL; auth; sandbox orchestration; assessment backend; Gitea API; releases |
| Core B Shabab Ahmed | Product and frontend | Next.js UI; EN/BN structure; lesson/mission flows; xterm client; reports; instructor dashboard; usability |
| Support Siam Ibne Sarwar | Selective QA, content, and documentation | Test cases; seed data; Bangla content review; setup guide; demo checklist; regression evidence |

## Assignment rules

- Jubair Ahmed Efty (Core A) and Shabab Ahmed (Core B) own every critical dependency even when Siam Ibne Sarwar (Support) helps with a subtask.

- Every task assigned to Siam Ibne Sarwar (Support) must have a clear input, output, deadline, and reviewer.

- Do not assign Siam Ibne Sarwar (Support) an authentication design, database migration sequence, sandbox security boundary, or final release alone.

- The core member who did not write a change normally reviews it.

- Jubair Ahmed Efty, as Team Lead, owns milestone scope, integration gates, and faculty-demo readiness, not every line of code.

# 4. Branch, review, and integration workflow

Your separate-branch condition is preserved, with one safety correction: completed work is integrated continuously into develop, while main remains the stable release branch. Combining all long-lived branches only at the end would hide conflicts until the deadline.

| Branch | Purpose | What enters it |
| --- | --- | --- |
| main | Protected release branch | Only reviewed 50% and 100% release PRs |
| develop | Shared integration branch | Reviewed task PRs throughout the roadmap |
| core-a/<issue>-<slug> | Jubair Ahmed Efty's task branch | One bounded issue |
| core-b/<issue>-<slug> | Shabab Ahmed's task branch | One bounded issue |
| support/<issue>-<slug> | Siam Ibne Sarwar's supporting task branch | One selected supporting issue |

## Task-to-release flow

- Create or assign a GitHub Issue with acceptance criteria.

- Update local develop, then create the member's task branch.

- Implement only that issue; commit small, reviewable changes.

- Run tests, security checks, and the relevant local demonstration.

- Open a Pull Request into develop; another core member reviews it.

- Merge only after acceptance checks pass; delete the task branch.

- At a milestone gate, open one release Pull Request from develop into main.

- Tag the stable release (v0.5.0 or v1.0.0) and preserve demo evidence.

No direct push: No member pushes feature work directly to main. Main is updated through reviewed Pull Requests on 31 August and 21 September, with emergency fixes handled through reviewed hotfix branches.

## Commit and review conventions

- Branch from the latest develop, not from another member's personal branch.

- Use issue-linked names such as core-a/GS-12-auth-api.

- Use clear commits such as feat: add mission start endpoint or test: cover assessment failure.

- A PR description must state summary, verification, risks, screenshots/logs, and Closes #<issue>.

- Reviewers check behavior, tests, security, maintainability, and scope - not only whether the code runs.

# 5. Dated roadmap: 1 August - 22 September

Jubair = Jubair Ahmed Efty (Core A / Team Lead), Shabab = Shabab Ahmed (Core B), and Siam = Siam Ibne Sarwar (Support). Gate days are deliberately reserved for integration, tests, and recovery. If a previous gate has not passed, do not start the next dependency-heavy phase.

## Phase 0 - Controlled restart and foundation

1-3 August

| Date | Assigned work | Required evidence / exit |
| --- | --- | --- |
| 1 Aug | All members: kickoff; confirm assigned roles; freeze MVP; archive/tag the pre-reset state; create the reset milestone, labels, and issues. Jubair (Core A): protect main; create develop; define branch policy. Shabab (Core B): confirm user journeys and required pages. Siam (Support): record environment and availability matrix. | Reset board, role map, scope statement, branch protections |
| 2 Aug | Jubair (Core A): scaffold API, Prisma, PostgreSQL, and Docker Compose baseline. Shabab (Core B): scaffold Next.js/Tailwind app and shared layout. Siam (Support): write setup checklist and collect version outputs. | Both apps boot; lockfiles and .env.example exist |
| 3 Aug | Jubair (Core A): add API /health, DB health check, lint/test scripts. Shabab (Core B): add web health screen and API client boundary. Siam (Support): follow setup from a clean clone and report gaps. Gate: merge reviewed foundation PRs into develop. | Clean-clone setup passes on both core machines |

## Phase 1 - Application foundation

4-10 August

| Date | Assigned work | Required evidence / exit |
| --- | --- | --- |
| 4 Aug | Jubair (Core A): define API conventions, error shape, auth threat model, and initial schema. Shabab (Core B): define routes, navigation, loading/error states, and responsive shell. Siam (Support): convert acceptance criteria into test cases. | Architecture decision record and UI route map |
| 5 Aug | Jubair (Core A): implement Prisma schema, first migration, seed process, and repository layer. Shabab (Core B): build login/register forms and validation states. Siam (Support): validate seed data and setup instructions. | Migration up/down path and repeatable seed |
| 6 Aug | Jubair (Core A): implement password hashing, login/logout, secure cookie/token handling, and auth tests. Shabab (Core B): build authenticated layout and session state. Siam (Support): test invalid credentials and duplicate account cases. | Auth API tests pass; no plaintext passwords/tokens |
| 7 Aug | Jubair (Core A): add student/instructor role guards and consistent errors. Shabab (Core B): integrate auth UI with API and route protection. Siam (Support): run role-access test matrix. | Student and instructor access rules verified |
| 8 Aug | Jubair (Core A): add Lesson, Mission, Attempt, and Progress models plus APIs. Shabab (Core B): build lesson and mission catalogue pages. Siam (Support): prepare small Git Basics content sample. | Seeded lesson and mission visible through API |
| 9 Aug | Jubair (Core A): add mission-start contract and attempt persistence. Shabab (Core B): build mission detail/start flow and EN/BN content structure. Siam (Support): review Bangla wording and empty/error states. | Student can start an attempt from the UI |
| 10 Aug | Gate: integrate all Phase 1 PRs; run migrations, API tests, UI smoke tests, and clean-clone setup. Use remaining time only for blockers. | Foundation gate passes on develop |

## Phase 2 - Safe practice terminal

11-17 August

| Date | Assigned work | Required evidence / exit |
| --- | --- | --- |
| 11 Aug | Jubair (Core A): write sandbox threat model and lifecycle API contract. Shabab (Core B): define terminal UX, reconnect, timeout, and error states. Siam (Support): prepare security/cleanup checklist. | Approved sandbox boundary and session states |
| 12 Aug | Jubair (Core A): build pinned sandbox image with non-root user and required Git tools. Shabab (Core B): build terminal container and status controls. Siam (Support): verify image build steps from documentation. | Reproducible non-root sandbox image |
| 13 Aug | Jubair (Core A): implement create/start/stop/destroy lifecycle, ownership checks, TTL, CPU/memory/PID limits, and cleanup. Shabab (Core B): connect mission start/stop UI states. Siam (Support): test cleanup and duplicate-start cases. | One isolated container per authenticated attempt |
| 14 Aug | Jubair (Core A): implement authenticated WebSocket/PTY bridge and server-side session mapping. Shabab (Core B): create client connection service. Siam (Support): test rejected unauthenticated connections. | Terminal stream works only for its owner |
| 15 Aug | Jubair (Core A): handle exit, resize, timeout, and orphan cleanup. Shabab (Core B): integrate xterm.js input/output, fit, focus, and resize. Siam (Support): document reproducible terminal tests. | Interactive terminal works in the mission page |
| 16 Aug | Jubair (Core A): add reconnect/idempotency behavior and structured logs. Shabab (Core B): add loading, reconnect, failure, and completion UX. Siam (Support): test refresh and unexpected-close scenarios. | Refresh does not leak or duplicate sandboxes |
| 17 Aug | Gate: run isolation, resource, ownership, cleanup, and end-to-end terminal tests; merge only passing PRs. | Safe-practice terminal gate passes |

## Phase 3 - Mission, assessment, and progress vertical slice

18-24 August

| Date | Assigned work | Required evidence / exit |
| --- | --- | --- |
| 18 Aug | Jubair (Core A): create deterministic starter repository and reset mechanism. Shabab (Core B): write the guided Git mission steps and command hints. Siam (Support): verify instructions as a beginner. | Same mission start state on every run |
| 19 Aug | Jubair (Core A): define assessment rules from repository state and required workflow events. Shabab (Core B): design result, hint, retry, and completion UI. Siam (Support): create pass/fail edge-case matrix. | Explainable rule specification |
| 20 Aug | Jubair (Core A): implement evaluator, score/result API, and stable feedback codes. Shabab (Core B): connect Check Progress action and feedback display. Siam (Support): validate messages against failure cases. | Correct pass/fail result for known repository states |
| 21 Aug | Jubair (Core A): persist attempts, events, scores, and completion timestamps transactionally. Shabab (Core B): show persisted progress after refresh/login. Siam (Support): verify duplicate submissions remain safe. | Progress survives refresh and re-login |
| 22 Aug | Jubair (Core A): add retry/reset APIs and audit logs. Shabab (Core B): polish mission checklist, success state, and next action. Siam (Support): test reset and retry paths. | A failed attempt can recover cleanly |
| 23 Aug | Jubair (Core A): expand integration tests and error handling. Shabab (Core B): run responsive/accessibility checks on the complete flow. Siam (Support): execute beginner UAT and record defects. | Critical-path test suite and defect list |
| 24 Aug | Gate: demonstrate login -> lesson -> mission -> sandbox -> Git work -> assessment -> stored progress from develop. | First complete single-user vertical slice |

## Phase 4 - 50% stabilization and faculty demonstration

25 August-1 September

| Date | Assigned work | Required evidence / exit |
| --- | --- | --- |
| 25 Aug | Jubair (Core A): add instructor attempt-list API with authorization. Shabab (Core B): build basic instructor attempt view. Siam (Support): prepare seeded demo accounts and attempts. | Instructor can inspect the demonstration attempt |
| 26 Aug | Jubair (Core A): improve API validation, error logs, and cleanup visibility. Shabab (Core B): fix responsive, keyboard, empty, and failure states. Siam (Support): proofread visible content. | No known blocker in the primary demo path |
| 27 Aug | Jubair (Core A): run auth, database, sandbox, and assessment integration tests. Shabab (Core B): run UI smoke/accessibility tests. Siam (Support): run the scripted demo from a clean browser. | Recorded test evidence and prioritized defects |
| 28 Aug | All members: integration/buffer day. Fix only P0/P1 defects. Rebuild from a clean clone and confirm seed/recovery steps. | Release candidate starts repeatably |
| 29 Aug | All members: 50% feature freeze. Stabilize data, copy, logs, and demo accounts. No new feature PRs. | Frozen v0.5 candidate |
| 30 Aug | All members: complete two timed rehearsals; test projector/network assumptions; prepare screenshots, a short fallback recording, and restart commands. | Demo checklist and fallback pack |
| 31 Aug | Jubair (Team Lead): open release PR develop -> main. Jubair + Shabab (Core A and Core B): review, run release checks, merge, tag v0.5.0. Siam (Support): verify submission notes and evidence. | Stable v0.5.0 on protected main |
| 1 Sep | All members: deliver 50% demonstration from main; record faculty feedback as new issues; do not implement changes during the demo. | 50% milestone accepted or feedback captured |

## Phase 5 - Gitea collaboration foundation

2-8 September

| Date | Assigned work | Required evidence / exit |
| --- | --- | --- |
| 2 Sep | All members: triage faculty feedback; protect the final MVP scope; assign only required changes. Jubair + Shabab (Core A and Core B): rebase planning on v0.5.0. | Final-half backlog and priorities |
| 3 Sep | Jubair (Core A): add pinned Gitea service, health checks, persistent data, and secret handling. Shabab (Core B): design team/lobby screens. Siam (Support): validate Gitea startup guide. | Gitea starts reliably inside the local stack |
| 4 Sep | Jubair (Core A): implement typed Gitea API client, health/retry handling, and test repository creation. Shabab (Core B): create collaboration service boundary in the UI. Siam (Support): document manual verification. | Idempotent test repository provisioning |
| 5 Sep | Jubair (Core A): add Team, Membership, CollaborationMission, and RepositoryLink models. Shabab (Core B): build team view and mission assignment states. Siam (Support): prepare deterministic team seed data. | Seeded two-student team and mission |
| 6 Sep | Jubair (Core A): provision Gitea users/tokens/repositories safely and idempotently. Shabab (Core B): integrate team mission launch. Siam (Support): test reruns and partial failures. | Repeatable provisioning without duplicate resources |
| 7 Sep | Jubair (Core A): connect sandbox Git remote to restricted internal Gitea network. Shabab (Core B): show member role, repository, and next workflow step. Siam (Support): run two-browser collaboration smoke test. | Two students can access the assigned repository |
| 8 Sep | Gate: demonstrate team creation, repository provisioning, and two member sessions. Fix only integration blockers. | Collaboration foundation gate passes |

## Phase 6 - Workflow assessment, reports, and feature freeze

9-15 September

| Date | Assigned work | Required evidence / exit |
| --- | --- | --- |
| 9 Sep | Jubair (Core A): define rules for branch, commit, push, pull request, review, and merge. Shabab (Core B): design collaboration progress timeline. Siam (Support): create valid/invalid workflow cases. | Deterministic collaboration rule set |
| 10 Sep | Jubair (Core A): ingest Gitea workflow state through a secured webhook or bounded polling service. Shabab (Core B): surface live/refreshable team status. Siam (Support): verify replay/duplicate events. | Reliable workflow event/state capture |
| 11 Sep | Jubair (Core A): implement team and individual scoring with explainable rule results. Shabab (Core B): implement score breakdown and corrective feedback. Siam (Support): validate scoring fixtures. | Same workflow always produces the same score |
| 12 Sep | Jubair (Core A): add individual report API and authorization. Shabab (Core B): build student history/report page. Siam (Support): test missing/partial attempts. | Student can view own evidence and feedback |
| 13 Sep | Jubair (Core A): add team report API. Shabab (Core B): build team contribution and workflow report. Siam (Support): verify report wording and evidence links. | Team report reflects both members accurately |
| 14 Sep | Jubair (Core A): add instructor filters, retry/reset operations, and audit trail. Shabab (Core B): complete instructor dashboard. Siam (Support): run instructor UAT. | Instructor can observe and recover a mission |
| 15 Sep | Jubair + Shabab (Core A and Core B): finish EN/BN feedback integration and all required UI/API error paths. Siam (Support): final Bangla/content review. Gate: feature freeze at end of day. | All required MVP features complete on develop |

## Phase 7 - Hardening, release, and 100% demonstration

16-22 September

| Date | Assigned work | Required evidence / exit |
| --- | --- | --- |
| 16 Sep | Jubair (Core A): full API/database/integration regression suite. Shabab (Core B): full UI and two-browser end-to-end suite. Siam (Support): maintain defect log and retest fixes. | No open P0; P1 owners and deadlines assigned |
| 17 Sep | Jubair (Core A): verify auth, authorization, secrets, sandbox limits, network boundaries, cleanup, and concurrency. Shabab (Core B): verify session expiry and safe error UX. Siam (Support): execute security checklist. | Security and resource controls evidenced |
| 18 Sep | All members: recovery/buffer day. Test failed services, orphan containers, duplicate webhooks, database backup/restore, and clean restart. | Documented recovery paths work |
| 19 Sep | Jubair (Core A): finalize reproducible deployment and seed/release scripts. Shabab (Core B): finalize user-facing help and empty states. Siam (Support): finalize setup and troubleshooting guide. | Fresh-machine deployment runbook |
| 20 Sep | All members: formal UAT using student and instructor scenarios; finalize report, diagrams, screenshots, and known limitations. | Signed UAT checklist and submission package |
| 21 Sep | Jubair (Team Lead): release PR develop -> main. Jubair + Shabab (Core A and Core B): review, test, merge, and tag v1.0.0. All members: two timed rehearsals from a clean restart. | Stable v1.0.0 and verified demo backup |
| 22 Sep | All members: deliver 100% faculty demonstration and submit code, documentation, and required evidence from the tagged release. | Final GitStack MVP submitted |

# 6. Demonstration scripts and release gates

## 1 September - 50% demonstration

The 50% milestone is a coherent vertical slice, not a claim that exactly half of every feature is complete. The faculty should see the product's central learn-practise-assess loop working from the tagged v0.5.0 release.

- Start the complete local stack using the documented release command.

- Log in as a student and open the small Git Basics lesson.

- Start the deterministic single-user mission.

- Use the browser terminal to complete the required Git actions.

- Run Check Progress and show explainable success or correction feedback.

- Refresh or re-login and show that the attempt and completion persist.

- Log in as the instructor and show the basic attempt list.

- State clearly that the Gitea collaborative mission is scheduled for the final half.

## 22 September - 100% demonstration

- Start from the tagged v1.0.0 release and show health checks.

- Show student and instructor roles and the EN/BN experience.

- Run the safe single-user mission and its automatic assessment.

- Open two student sessions for one assigned Gitea-backed team mission.

- Demonstrate branch, commit, push, pull request, review, and merge evidence.

- Show deterministic individual and team scores with corrective feedback.

- Show student history, team report, and instructor dashboard.

- Show retry/reset behavior and explain sandbox isolation, limits, and cleanup.

- Finish with known limitations and the reproducible setup/runbook.

## Demo safety pack

- Pinned release tag, lockfiles, images, migrations, and seed data.

- Pre-created demo accounts with no real personal information.

- Exact startup, health-check, reset, and shutdown commands.

- A short fallback recording and screenshots created from the same release.

- A local copy of documentation in case internet access fails.

- A clean backup database or repeatable seed - never an unverified live data dump.

# 7. Definition of Done, quality controls, and risks

## Definition of Done for every implementation issue

- Acceptance criteria are written before implementation.

- The branch starts from current develop and contains only the assigned scope.

- Code includes appropriate validation, error handling, and tests.

- No secrets, tokens, passwords, database dumps, or generated clutter are committed.

- The author runs and records the relevant verification.

- A core teammate reviews the PR and all blocking comments are resolved.

- Required documentation, migrations, seed updates, and screenshots/logs are included.

- The PR is merged into develop, the issue is closed, and the task branch is deleted.

## Security minimum for the browser terminal

- Run as a non-root user; never use privileged containers.

- Drop unnecessary Linux capabilities and apply CPU, memory, PID, time, and storage limits.

- Do not mount host directories, secrets, or the Docker socket inside student containers.

- Authorize every terminal/sandbox request against the owning user and attempt.

- Disable external network access by default; allow only the restricted internal Gitea path when required.

- Destroy expired/orphaned containers and make lifecycle operations idempotent.

- Do not expose this prototype publicly until the sandbox boundary receives a dedicated security review.

## Risk register

| Risk | Failure mode | Control | Owner |
| --- | --- | --- | --- |
| Academic pressure | Missed tasks and rushed merges | WIP limit; buffer/gate days; cut optional scope early | Jubair Ahmed Efty (Team Lead) |
| Late integration | Conflicts discovered near demos | Task PRs into develop; release PRs into main | Jubair Ahmed Efty + Shabab Ahmed |
| Docker/Gitea instability | Demo cannot start | Pinned versions, health checks, clean-clone test, fallback pack | Jubair Ahmed Efty (Core A) |
| Unsafe sandbox | Host or data exposure | Non-root, limits, no host mounts/socket, ownership checks | Jubair Ahmed Efty (Core A) |
| Assessment ambiguity | Incorrect or unfair scores | Evaluate deterministic Git state/events; fixtures and explainable rules | Jubair Ahmed Efty + Siam Ibne Sarwar |
| Support unavailable | Critical task blocked | Support owns only bounded, non-critical tasks | Jubair Ahmed Efty (Team Lead) |
| Feature creep | Core flow remains incomplete | Freeze required scope; apply cut order below | Jubair Ahmed Efty (Team Lead) |
| Secrets in Git | Credential compromise | .env.example, secret scanning, rotation, review checklist | All members |

## Scope-cut order if the team slips

- Remove visual effects, theme extras, and non-essential animations.

- Reduce the lesson catalogue to the smallest coherent set.

- Keep one single-user mission and one collaborative mission only.

- Remove badges, leaderboards, advanced analytics, and optional filters.

- Use seeded instructor accounts instead of building non-essential account administration.

- Do not cut sandbox isolation, authentication, deterministic assessment, persistence, critical tests, or release documentation.

# 8. How the team will work with ChatGPT during execution

This roadmap is meant to be executed one issue at a time. I will guide the team through setup, commands, implementation decisions, tests, PR review, and gate verification without treating old work as completed evidence.

## What to send at the start of a task

- The date, phase, issue title, assigned member, and acceptance criteria.

- The output of git status and git branch --show-current.

- Relevant project files or exact terminal errors - never passwords or tokens.

- Whether the request is learning, diagnosis, implementation, or review.

## What I will provide

- The smallest safe next step with an explanation of why it is needed.

- Exact commands or code only after confirming the repository state.

- Verification steps, expected output, edge cases, and rollback/recovery advice.

- PR title/description, review checklist, and milestone exit decision.

- A warning when a proposed shortcut creates security, merge, or deadline risk.

Execution rule: Do not jump ahead to a later phase because one screen looks finished. Pass the current phase gate first, then start the next dependency.

# 9. First-day checklist - 1 August 2026

The roadmap begins with decisions and repository controls, not feature coding. Complete these items in one team session before anyone creates an implementation branch.

- Confirm the assigned roles: Jubair Ahmed Efty as Core A / Team Lead, Shabab Ahmed as Core B, and Siam Ibne Sarwar as Support.

- Confirm realistic weekly hours and academic blackout dates.

- Agree that pre-1-August work is reference only, while repository history remains preserved.

- Archive/tag the pre-reset baseline and create the new reset milestone/project view.

- Freeze the required MVP and the scope-cut order.

- Protect main, create develop, and require reviewed Pull Requests.

- Create the Phase 0 and Phase 1 issues with owners and acceptance criteria.

- Record compatible Node.js, package-manager, Docker, Compose, and database tooling.

- Confirm both core machines can clone and authenticate safely.

- Schedule the 10 August, 17 August, 24 August, 31 August, 8 September, 15 September, and 21 September gates.

First message to send me: "Start GitStack Roadmap - 1 August. Core A and Team Lead is Jubair Ahmed Efty, Core B is Shabab Ahmed, and Support is Siam Ibne Sarwar. Our available hours are [...]. Guide us through the kickoff checklist one step at a time."

## Final recommendation

Use this roadmap as the scope contract. Keep personal branches short, integrate reviewed work into develop continuously, release to protected main at the two mandatory demonstrations, and defend the narrow vertical slice before adding breadth. This is the most reliable way for a two-core-member team to meet both deadlines without repeating the previous schedule failure.